## Score Card
Score Card |  | Current Impact | Likelihood | Type | Current Impact | Issue | Current Impact | Likelihood | Internal / External
Total Risks Identified | 12 | Critical | High | All | Critical | Yes | Critical | High | Internal
Number of Current Critical Risks | 0 | Current Impact | Likelihood | Type |  |  | Current Impact | Likelihood | Internal / External
Critical Risks with High Likelihood | 0 | Critical | High | Requirements |  |  | Critical | High | External
Critical Issues | 0 | Current Impact | Likelihood | Type
|  | Critical | High | Resources
Critical Risks with High Likelihood by Category |  | Current Impact | Likelihood | Type
All | 2 | Critical | High | Social-Political
Requirements | #REF! | Current Impact | Likelihood | Type
Resources | 0 | Critical | High | Technology
Social-Political | 0
Technology | 0
Critical Risks with High Likelihood Internal or External
Internal | 0
External | 0

## Consolidated Risks
Risk ID | Precept | Governance point | Risk | Original Impact | Current Impact | Original Likelihood | Current Likelihood | Likelihood | Issue | Type | Internal / External | Comment | Mitigations
R01 | Measures must exist to ensure consistency and quality of the FHIR specification | QA process | FHIR resource specifications are not of consistent representation and quality |  |  | 0% | 0% | Low |  |  |  |  | M01.1 Principles of resource approval form specifications are clearly documented. M01.2 Development of methodology and design principles M01.3 Provide specific metrics for assessing quality of specifications (Principle: “definitional thoroughness”) and apply QA processes M01.4 Conformity tooling exists for production of ballot-able specifications
R02 | FHIR specifications should be "fit for purpose" and readily adaptable for use with other established HIT Standards |  | The customers (end users) of FHIR implementers do not agree that resources are represented correctly or that they are used appropriately. |  |  | 0% | 0% | Low |  |  |  |  | M02.1 Implementers can contribute to, and have ready access to, a public listing of known implementation concerns and issues along with proposed or actual dispositions and associated FHIR versions. (Note: this is a separate process from the balloting process, and could / should be an input to subsequent balloting of affected versions) M02.2 Collaborative and broad review of input from other standards bodies on FHIR material M02.3 All published FHIR specifications include a disclaimer that places the burden of verifying the specifications are “fit for purpose” with the implementer and expresses the objective of simplifying and accelerating implementation by reducing complexity of the data structures where reasonable. See http://wiki.hl7.org/index.php?title=Fundamental_Principles_of_FHIR. M02.4 “Implementation Frameworks” are defined, clearly documented, and readily discoverable.
R03 | FHIR specifications should be "readily implementable" and produce easy to implement, fully valid FHIR instances |  | FHIR specifications are incorrectly or inconsistently implemented, requiring customization for paired interfaces, preventing or reducing the ability to achieve “plug and play” portability across vendor solutions. |  |  | 0% | 0% | Low |  |  |  |  | M03.1 See M02.1 M03.2 Conformity Tooling exists to allow implementers to self-assess their conformity to the specification M03.3 Conformity Tooling exists for consumers of FHIR-based interfaces to test conformity of vendors’ solutions M03.4 Conformity assertions are sufficiently granular and testable to allow certification of static resource models used in vendors’ interfaces M03.5 Dynamic behaviour patterns are modeled in implementation frameworks and working examples provided M03.5 Conformity assertions are sufficiently granular and testable to allow certification of dynamic behaviours using FHIR resources
R04 | The FHIR specification is open, yet the broadest benefit is derived from everyone using the same FHIR |  | FHIR community will be divided into two or more FHIR communities internationally, each with a somewhat different specification. |  |  | 0% | 0% | Low |  |  |  |  | M04.1 Transparency of enhancement to the specification M04.2 Maintain a truly open environment within HL7 that encourages the broadest range of participants M04.3 Provide a responsive governance process that deals with customer issues and concerns
R05 | HL7 seeks to be the leader and the "home" for the FHIR specification targeted in healthcare. |  | Demand for FHIR resources / specifications outstrip HL7’s organizational capacity to produce them. |  |  | 0% | 0% | Low |  |  |  |  | M05.1 Involve new participants in the production of the FHIR specification M05.2 Minimize the barriers to access by new participants
R06 | To be successful within HL7, the FHIR specification should have broad support and participation |  | HL7 Organizational capacity for creation and maintenance of FHIR assets does not extend beyond the core team (and / or core team members get hit by a bus or some other unfortunate incident) |  |  | 0% | 0% | Low |  |  |  |  | M06.1 Encourage WGs to take an active role in the development of FHIR specifications within their sphere of expertise M06.2 Develop FHIR competency in as many members of the Working Group as desire it M06.3 Reduce the FHIR resource and profile "responsibilities" of the core team wherever possible M06.4 Reduce the production FHIR "responsibilities" of the core team wherever possible
R07 | FHIR will be implementable in a variety of technologies |  | FHIR specifications may become too rigidly associated with a specific technology (e.g. RESTful interfaces) only. |  |  | 0% | 0% | Low |  |  |  |  | M07.1 Implementation guides must (should?) incorporate examples of use of resources in different implementable interoperability paradigms including messaging, structured documents, and services.
R08 | To be successful, the potential FHIR user community must have a proper understanding of the balance between flexibility and usability within the frequently complex healthcare domain |  | Different communities will have perceptions about FHIR that will discourage its appropriate use. (i.e.) FHIR is too simple /complicated to use; FHIR is too loose, and implementations won't be able to interoperate; FHIR is too tight, and won't be able to used to solve real world problems; works for mobile and not anything else | Serious |  | 0% | 0% | Low |  |  |  |  | M08.1 Recognize these perceptions at the outset and provide appropriate guidance for those seeking information M08.2 Map (demonstrate, exemplify) areas where these perceptions are mitigated by actual working implementations. This responsibility for mapping and exposing examples must be actively assigned to someone during the development process. M08.3 Ensure traceability from clearly defined requirements to actual specifications
R09 | FHIR development process must be capable of meeting appropriate timelines for the implementers |  | FHIR development process will slow down to not meet implementers' time requirements (scope creep, committee churn, lack of principals or thought leaders stall progress) | Serious | Serious | 0% | 0% | Low |  |  |  |  | M10.1 Connectathons provide a mechanism for addressing proposals and responses in a timely manner M10.2 Online tracker allows submission of comments any time M10.3 Ballot/Comment reconciliation facilitated by block voting recommendations presented by subcommittee M10.4 Rigorous Issue resolution and WG discussion facilitation by co-chair M10.5 Explicit documentation and knowledge transfer enable continuity M10.6 Archivist tasks explicitly assigned M10.7 Core team taking on responsibility for resources at high risk for committee churn (e.g. Patient Admin)
R10 | FHIR aims to enable interoperability across the health care spectrum |  | Concern that the scope of technology and/or of data may be too broad and therefore unrealizable |  |  | 0% | 0% | Low |  |  |  |  | M11.1 Definition of scope of use and the scope of data/content must be expressed. M11.2 Scope must be endorsed and enforced by governance and management processes. M11.3 FHIR undertakes definition of artifacts only when there is a strong likelihood of near-term implementation. M11.4 FHIR will only define artifacts at the international level when at least 1% of the international community is likely to make use of them. (The 'Other' Resource or realm profiles will satisfy remote edge case requirements)
R11 | "80/20 rule" - FHIR process and content should not become mired in issues of interest only to a few stakeholders |  | Perceptions that the HL7 process favors theoretical issues over practical issues Disagreement becomes institutionalized in the specification because consensus cannot be gained The specification becomes overwhelmed with content used only by a few parties | Serious | Serious | 0% | 0% | Low |  |  |  |  | M12.1 In-Scope use cases must be explicitly identified and Out-of-Scope use cases must be documented as they arise M12.2 Describe the use of extensions for out-of-scope use cases M12.3 Use of extensions in HL7 development allows users to see that we "practice what we preach"
Note on D11: Lynn: Concern that the scope of technology and/or of data may be too broad and may be unable to meet overall objectives (FHIR is trying to do too much; FHIR will be a step too far for the existing communities)
Note on B12: Lynn: http://www.healthintersections.com.au/?p=1924; - FHIR focuses on broadly supported capabilities and leaves "edge cases" to extensibility mechanisms; keeping edge-cases and disagreement out of the specification. It’s about making the complexity live where it belongs. Properly formulated, the 80/20 rule is that "FHIR only includes an element if 80% of systems implement it."